## 48-Motokros
Site name | Motokros
Number | 48
Cadastral area | Hrubá Vrbka
Coordinates | 48°51'29.827"N, 17°27'27.125"E
Location link | https://mapy.cz/s/lujubucoha
Target species | stag beetle
Target habitats | pasture
Planned area of the site (potential) | 2 ha
Area for the given year TOTAL (ha) | 2 ha
Site characteristics: Former pasture on a north-inclined slope, with scattered vegetation, abandoned thirty years ago, with random selective management. An area near Čertoryje National Nature Reserve. Subsequent grazing will change the character of the surrounding existing habitat, thereby increasing biodiversity. Systematic clearing of the site started in 2017 by the Czech Union for Nature Conservation (ČSOP) Bílé Karpaty (under Action C.2). However, after the land improvements, the lease agreement was terminated, which was not renewed at the will of the owner. The negotiations with the new user were complicated, but in the end it was possible to restore the original plan and the management of the site continues.
Anticipated management: Self-seeding plant removal leading to the creation of a pasture.
Implemented/planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023-2028
Intervention | more than 20 years without intervention; since 2018 the site restored by the ČSOP |  | self-seeding plant removal | regrowth mowing | regrowth mowing | without management | regrowth mowing | grazing
Deadline |  | 2018: 11/2018; 2019: 8-10/2019; 2020: 8-10/2020; 2022: 7-11/2022
Area |  |  | 1 | 2 | 2 |  | 1.221 | 1.3
Intervention
Deadline
Area
TOTAL interventions |  | 0 | 0 | 0 | 0 | 0 | 1.221 | 1.3