## List1
Site name | Lušová
Number | 8
Cadastral area | Nový Hrozenkov
Coordinates | 49.3513769N, 18.1545156E
Location link | https://mapy.cz/letecka?vlastni-body&x=18.1542153&y=49.3511951&z=16&ut=Lu%C5%A1ov%C3%A1&uc=9pgwXx8nOW&ud=49%C2%B021%274.957%22N%2C%2018%C2%B09%2716.256%22E
Target species | large blue, dusky large blue
Target habitats | thyme pasture
Planned area of the site (potential) | 1.7
Area for the given year TOTAL (ha) | 1.7
Site characteristics: The main site has a south-west exposure and is very rich. In the upper part there is a juniper pasture with thyme, the lower part is wetter and there is a spring. The upper part is overgrown. The site has long been managed by mowing outside conservation activities.
Anticipated management: Mosaic-like mowing by hand during August-September. Clearing outside the growing season.
Implemented/planned management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing | hand mosaic mowing
Deadline | 7/2016 | 8-9/2017 | 8-9/2018 | 8-9/2019 | 8-9/2020 | 8-9/2021 | 8-9/2022 | 8-9/2023 | 8-9/2024 | 8-9/2025 | 8-9/2026 | 8-9/2027 | 8-9/2028
Area | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2
Intervention | The site was mowed once before the start of the project. Due to the potential for target species occurrence, it has been included in the project since 2017 and management has been changed in order to create the most optimal conditions for occurrence and reproduction of the large blue butterfly in particular. | 2019: clearing
Deadline |  | 2019: 10/2019
Area |  | 2019: 0.7
Intervention
Deadline
Area
TOTAL interventions | 1.2 | 1.2 | 1.2 | 1.9 | 1.7 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2