## Uherská
Site name | Uherská
Number | 4
Cadastral area | Huslenky
Coordinates | 49.2838078N, 18.1005475E
Location link | https://mapy.cz/s/2IUYa
Target species | large blue (on site)
Target habitats | pasture
TOTAL area | 2.3729
Site characteristics (condition at the start of project): Most of the site is south/south-west exposure. In the part under the wires, scattered junipers grow. Part of the site was a stone quarry in the past. This is a dry habitat and therefore does not overgrow very quickly. Occurrence of thyme.
Anticipated management (condition at the start of project): Clearing especially around the perimeter of the site and then in the part that connects the two parts of the site and is overgrown with self-seeding conifers. Annual extensive grazing by sheep, optimally outside the summer holidays (otherwise leaving part of the area ungrazed). Leaving suitable solitary bushes in the area.
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | 2017: /; 2018: clearing
Deadline | about 3 (?) years without intervention | 2018: 4/2018
Area | 1.8 | 2018: 0.06
Intervention | Grazing in the past, all previous activities were carried out by the landowner outside of conservation activities. | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline |  |  | 9,10/2018 | 10,11/2019 | 11,12/2020 | 11/2021 | 11/2022 | 6/2023 | 10/2024 | 9/2025 | 6/2026 | 10/2027 | 9/2028
Area |  |  | 2.3729 | 2.3729 | 2.3729 | 2.3729 | 2.3729 | 2.3729 | 2.3729 | 2.3729 | 2.3729 | 2.3729 | 2.3729
Intervention |  | / |  | mowing of regrowth (ungrazed vegetation) |  | 11/2021: clearing - partial clearance of the area; 11/2022: mowing of regrowth (ungrazed vegetation); 9/2025: mowing of regrowth (ungrazed vegetation); 9/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  |  | 11/2019 |  | 11/2021: 4/2021; 11/2022: 4/2022; 9/2025: 10/2025; 9/2028: 10/2028
Area |  |  |  | 2.3729 |  | 11/2021: 0.6; 11/2022: 2.3729; 9/2025: 2.3729; 9/2028: 2.3729
Intervention |  | / | yellow-rattle sowing | thyme planting |  | 11/2021: thyme planting
Deadline |  |  | 11/2018 | 11/2019 |  | 11/2021: 6/2021
Area |  |  | 0.91 | 120 pcs |  | 11/2021: 50 pcs
TOTAL interventions | 1.8 | 0 | 3.3429 | 4.7458 | 2.3729 | 2.9729 | 4.7458 | 2.3729 | 2.3729 | 4.7458 | 2.3729 | 2.3729 | 4.7458