## 10-Pod Hribovňou
Site name | Pod Hribovňou
Number | 10
Cadastral area | Vyškovec
Coordinates | 48.9331161N, 17.8445314E
48.9293275N, 17.8392314E
Location link | https://mapy.cz/s/puhuravejo
https://mapy.cz/s/ranosemuve
Target species | clouded Apollo
Target habitats | grazing grove
Planned area of the site (potential) | 8 ha
Area for the given year TOTAL (ha) | 5.074 ha
Site characteristics: Two separate sites, separated by Hribovňa ridge. The first part inclined to the north lies for the most part in Pod Hribovňou Natural Monument. Here, in 2016, on an area of 0.607, the regrowth was mowed, followed by grazing from the LMP grant title. The rest of the area has been abandoned for 40-50 years. The second, more sloping part of the site is oriented to the north-west and on most of the area there are self-seeding plants more than 40 years old. There is an abundance of clouded Apollo in the vicinity.
Anticipated management: Opening the existing vegetation and removal of a substantial part of the regrowing shrubs with the aim of creating a more open grazing grove. Subsequent management will take place by grazing followed by mowing of ungrazed vegetation.
Implemented/planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023-2028
Intervention | grazing from PPK grant title |  | grazing | grazing | grazing | grazing | grazing | grazing
Deadline | 2017 |  | 10-12/2018 | 6-8/2019 | 6-8/2020 | 6-8/2021 | 6-8/2022
Area - Kročilová Mo | 0.607 |  | 0.607 | 0.615 | 0.615 | 0.615 | 0.548 | 0.615
Intervention | more than 40 years without management |  |  | self-seeding plant clearing | self-seeding plant clearing | merged with the plot below | merged with the plot below | merged with the plot below
Deadline |  | 2019: 10-12/2019; 2020: 10-12/2020
Area - Hodulík |  | 2019: 1.178; 2020: 1.393
Intervention |  | 2020: grazing; 2021: grazing; 2022: grazing; 2023-2028: grazing
Deadline |  | 2020: 6-8/2020; 2021: 6-8/2021; 2022: 6-8/2022
Area - Hodulík |  | 2020: 1.178; 2021: 2.57; 2022: 2.581; 2023-2028: 0
Intervention |  | 2021: self-seeding plant clearing; 2022: hand mowing; 2023-2028: transfer to LPIS
Deadline |  | 2021: 6-8/2021; 2022: 6-8/2022
Area - Chovancová M |  | 2021: 0.738; 2022: 0.99; 2023-2028: 0
Intervention |  | 2021: grazing; 2022: grazing; 2023-2028: transfer to LPIS
Deadline |  | 2021: 6-8/2021; 2022: 6-8/2022
Area - Kročilová Ma |  | 2021: 0.642; 2022: 0.636; 2023-2028: 0
Intervention |  | 2021: regrowth; 2022: management paid by the owner; 2023-2028: management
Deadline |  | 2021: 6-8/2021
Area - Šimek |  | 2021: 0.266
TOTAL interventions |  |  | 0.607 | 1.793 | 3.186 | 4.831 | 4.755 | 0.615