## Grúň
Site name | Nová Bošáca - Grúň, Pod Grúňom, Predpoloma
Number | 1
Cadastral area | Nová Bošáca
Coordinates | 48.897953N, 17.796960E
Location link | https://goo.gl/maps/CMd6J7HrDE93Bpia8
Target species | Maculinea arion, Parnassius mnemosyne, Colias myrmidone, Lucanus cervus
Target habitats | pasture, forest pasture, coppice forest, change of management
TOTAL area | 59.25 ha
Site characteristics (condition at the start of project): The site is connected to the rarest areas in Biele Karpaty PLA in Lopeníček and Grúň natural monuments with the occurrence of rare species of orchids, butterflies and habitats (*6210, *7720, 6510), but also intensive pastures with cattle. There is also a continuous stand of beech and oak forests with Lucanus cervus, Rosalia alpina; spruce monoculture planted in many places, intensive logging. The affected areas were without management for a long time and heavily overgrown with self-seeding woody plants - hawthorn, blackthorn, oak, etc. Exposure of the slope: SE, S and SW, steeper slope. Access by local, field and forest roads, by off-road vehicle/tractor in dry weather, in frost.
Management during the project: Clearing continuous areas of self-seeding woody plants, leaving old trees originally located on pasture, leaving prospective young trees for scattered pasture, clearing forest edges, creating forest pastures, forest edges, glades, coppice forests. Grazing by cattle and sheep in cooperation with local stakeholders. Annual extensive grazing.
Planned management
| 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | without intervention - coppice forest | without intervention - coppice forest | without intervention - coppice forest | without intervention - coppice forest | without intervention - coppice forest | without intervention - coppice forest
Deadline | 0 | 0 | 0 | 0 | 0 | 0
Area | 10.76 | 10.76 | 10.76 | 10.76 | 10.76 | 10.76
Intervention | grazing | grazing | grazing | grazing | grazing | grazing
Deadline | 5-10/2023 | 5-10/2024 | 5-10/2025 | 5-10/2026 | 5-10/2027 | 5-10/2028
Area | 38.82 | 38.82 | 38.82 | 38.82 | 38.82 | 38.82
Intervention | mowing of regrowth and ungrazed vegetation | mowing of regrowth and ungrazed vegetation | mowing of regrowth and ungrazed vegetation | mowing of ungrazed vegetation | mowing of ungrazed vegetation | mowing of ungrazed vegetation
Deadline | 10-12/2023 | 02-03, 10-12/2024 | 02-03, 10-12/2025 | 10-12/2026 | 10-12/20267 | 10-12/2028
Area | 38.82 | 38.82 | 38.82 | 38.82 | 38.82 | 38.82
Intervention | mowing of extensified areas | mowing of extensified areas | mowing of extensified areas | mowing of extensified areas | mowing of extensified areas | mowing of extensified areas
Deadline | 6-9/2023 | 6-9/2024 | 6-9/2025 | 6-9/2026 | 6-9/2027 | 6-9/2028
Area | 9.67 | 9.67 | 9.67 | 9.67 | 9.67 | 9.67
Intervention
Deadline
Area
Intervention
Deadline
Area
TOTAL interventions | 87.31 | 87.31 | 87.31 | 87.31 | 87.31 | 87.31