## 23-Skaličí
Site name | Skaličí
Number | 23
Cadastral area | Žítková
Coordinates | 48.9928658N, 17.8749450E
Location link | https://mapy.cz/s/logajojara
Target species | clouded Apollo
Target habitats | grazing grove
Planned area of the site (potential) | 3 ha
Area for the given year TOTAL (ha) | 1.032
Site characteristics: East-facing location, on a part of the area with occasional management by the owner, leading to a slight local suppression of expanding self-seeding woody plants. The character of the site and the presence of mature trees allow the creation of a grazing grove.
Anticipated management: Opening the vegetation, leading to the creation of a grazing grove. After clearing self-seeding plants, the area will be integrated into the existing surrounding pastures and regularly grazed.
Implemented/planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023-2028
Intervention | occasional management on part of the area by the owner | 2019: self-seeding plant clearing; 2022: mowing; 2023-2028: transfer to LPIS
Deadline | 2017 | 2019: 9-11/2019; 2022: 7-9/2022
Area | about 0.3 | 2019: 0.804; 2022: 0.27
Intervention |  | 2020: grazing; 2021: grazing; 2022: grazing; 2023-2028: transfer to LPIS
Deadline |  | 2020: 7-9/2020; 2021: 7-9/2021; 2022: 7-9/2022
Area |  | 2020: 0.804; 2021: 0.86; 2022: 0.762
TOTAL interventions |  | 0 | 0 | 0.804 | 0.804 | 0.86 | 1.032 | 0