## 34-Bošačky
Site name | Bošačky
Number | 34
Cadastral area | Lopeník, Vyškovec
Coordinates | 48°55'55.850"N, 17°48'52.524"E
Location link | https://mapy.cz/s/cemuruhono
Target species | clouded Apollo, stag beetle
Target habitats | pasture, grazing grove, grazing forest
Planned area of the site (potential) | 15 ha
Area for the given year TOTAL (ha) | 22.771 ha
Site characteristics: Wider surroundings of former pastures around Predpolomský stream, in different degrees of succession, from slightly overgrown parts to about 40-year-old stands. The colourful mosaic of the entire area predetermines high-quality species biodiversity. Some areas of about 7 ha were in the LPIS records in the past, but after overgrowing with shrubs, they were excluded and abandoned due to their unsuitability. A site covering 0.5 ha was financed from LMP source until 2016.
Anticipated management: Self-seeding plant removal, leading to the formation of all three types of anticipated habitats. Regular extensive grazing will be introduced on most of the site. Part of the area will be transferred to LPIS after the first intervention.
Implemented/planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023-2028
Intervention | see site characteristics | 2020: self-seeding plant clearing; 2021: grazing; 2022: grazing; 2023-2028: transfer to LPIS or managed by the contractor
Deadline |  | 2020: 2-11/2020; 2021: 7-9/2021; 2022: 7-9/2022
Area |  | 2020: 13.178; 2021: 2.447; 2022: 11.202
Intervention | see site characteristics | 2021: mowing; 2022: mowing; 2023-2028: transfer to LPIS or managed by the contractor
Deadline |  | 2021: 7-9/2021; 2022: 7-9/2022
Area |  | 2021: 15.092; 2022: 2.086
Intervention | see site characteristics | 2021: self-seeding plant clearing; 2022: self-seeding plant clearing; 2023-2028: transfer to LPIS or managed by the contractor
Deadline |  | 2021: 2-11/2021; 2022: 2-11/2022
Area |  | 2021: 1.488; 2022: 1.256
TOTAL interventions |  | 0 | 0 | 0 | 0 | 19.027 | 14.544