## List1
Site name | Buchlov
Number | 1
Cadastral area | Huslenky
Coordinates | 49.3118175N, 18.1037789E
Location link | https://mapy.cz/turisticka?vlastni-body&x=18.1037790&y=49.3118594&z=17&ut=Buchlov&uc=9p-jQx8a9g&ud=49%C2%B018%2742.543%22N%2C%2018%C2%B06%2713.604%22E
Target species | large blue
Target habitats | thyme pasture
Planned area of the site (potential) | 3.6
Area for the given year TOTAL (ha) | 3.6
Site characteristics: A complex of meadows and pastures oriented to the west, south-west, south, and south-east. Between the meadows, there are old overgrown edge habitats that gradually connect. In the central site there is a relatively strong population of the large blue butterfly. On adjacent plots, the effort is to create suitable conditions for the target species so that it can spread from the central part.
Anticipated management: Part of the area is grazed in May, and then from the end of August to September with the help of sheep. The remaining area is mowed by hand from the end of August to the beginning of September. Scrub clearance are also planned, which would better connect the individual parts of the site.
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | mowing, grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing | sheep grazing
Deadline | 6,7,8/2016 | 5,8-9/2017 | 5,8-9/2018 | 5,8-9/2019 | 5,8-9/2020 | 5,8-9/2021 | 5,8-9/2022 | 5,8-10/2023 | 5,8-10/2024 | 5,8-10/2025 | 5,8-10/2026 | 5,8-10/2027 | 5,8-10/2028
Area | 2.7 | 1.3 | 1.3 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4
Intervention | The sites were gradually overgrown, but there was an effort by the owners to cultivate at least some areas, and carry out the most necessary management interventions, which were not too intensive. Earlier interventions on the site were carried out for the benefit of burnt orchid, fringed gentian, and early purple orchid. With the start of the project in 2017, the site was evaluated as potentially suitable and expanded. Innovative management took place here, the grazing area was increased, and limited scrub clearing started. | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing
Deadline |  | 8-9/2017 | 8-9/2018 | 8-9/2019 | 8-9/2020 | 8-9/2021 | 8-9/2022 | 8-9/2023 | 8-9/2024 | 8-9/2025 | 8-9/2026 | 8-9/2027 | 8-9/2028
Area |  | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2
Intervention |  | 2017: scrub clearing; 2018: scrub clearing; 2019: scrub clearing
Deadline |  | 2017: 9-10/2017; 2018: 9-10/2018; 2019: 9-10/2019
Area |  | 2017: 0.1; 2018: 0.2; 2019: 0.12
TOTAL interventions | 2.7 | 3.6 | 3.7 | 3.72 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6