## Kamenné
Site name | Kamenné
Number | 10
Cadastral area | Dolní Bečva
Coordinates | 49.4672658N, 18.2272269E
Location link | https://mapy.cz/s/haholefume
Target species | large blue (on site)
Target habitats | pasture
TOTAL area | 1.6211 ha
Site characteristics (condition at the start of project): Two side-by-side but separate parts, the southern and south-western slopes. Most of the site has been repeatedly managed (grazing) in the previous five years, newly added adjacent parts overgrown mainly with self-seeding trees, partially overgrown with ferns. Accessible from the road running at the lower boundary of the site.
Anticipated management (condition at the start of project): Extending the original smaller site by clearing around the perimeter, in two places also by clearing the adjoining parts, leaving some trees and bushes (to provide shade/food/shelter for animals). Annual extensive grazing by sheep, optimally outside the summer holidays (otherwise leaving part of the area ungrazed).
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | 2017: /; 2018: /; 2019: clearing - partial clearance of the area
Deadline |  | 2019: 4,5/2019
Area | 1.2487 | 2019: 0.45
Intervention | The greater part of the site was part of the LIFE Beskydy project in 2014 - 2018 (LIFE12 NAT/CZ/000629), but with different management (focus on priority habitat of Nardus grasslands). | / | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline |  |  |  | 5,11/2019 | 6,11,12/2020 | 6/2021 | 6,10/2022 | 5/2023 | 9/2024 | 10/2025 | 6/2026 | 5/2027 | 9/2028
Area |  |  |  | 1.6211 | 2.7211 | 1.6211 | 1.6211 | 1.6211 | 1.6211 | 1.6211 | 1.6211 | 1.6211 | 1.6211
Intervention |  | / | / | mowing of regrowth (ungrazed vegetation) | mowing of regrowth (ungrazed vegetation) |  |  | 10/2025: mowing of regrowth (ungrazed vegetation); 9/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  |  | 5/2019 | 7/2020 |  |  | 10/2025: 5/2019; 9/2028: 10/2022
Area |  |  |  | 1.6211 | 1.1 |  |  | 10/2025: 1.6211; 9/2028: 1.6211
Intervention |  | / | / | thyme planting
Deadline |  |  |  | 9/2019
Area |  |  |  | 150 pcs
TOTAL interventions | 1.2487 | 0 | 0 | 3.6922 | 3.8211 | 1.6211 | 1.6211 | 1.6211 | 1.6211 | 3.2422 | 1.6211 | 1.6211 | 3.2422