## Hrbacek
Site name | Hrbáček
Number | 6
Cadastral area | Hovězí
Coordinates | 49.3135444N, 18.0620131E
Location link | https://mapy.cz/s/2IXbI | occurrence of ants of the Myrmica genus on the site, the occurrence of large blue at a distance of 100 m
Target species | large blue
Target habitats | pasture
TOTAL area | 1.7714 ha
Site characteristics (condition at the start of project): Predominantly south-eastern slope, trophic cultural meadow, last 2-3 years without intervention. An old orchard adjoins the site which is heavily overgrown with self-seeding woody plants. An interesting combination of a species-varied meadow, which can be greatly improved with suitable interventions, and an old orchard, which already represents a good habitat for various insects.
Anticipated management (condition at the start of project): Gradual clearing in part of the old orchard, where self-seeding woody plants will be removed and individual parts will be made available for grazing in the orchard area as well. Leaving old dead trees on the site. Extensive grazing by sheep on the meadow area in the first year. For an ideal condition, it is advisable to open up the bushes in the upper part. In addition, it will be necessary to implement regular mowing of the ungrazed vegetation due to the higher nutrient level of the site, especially in its lower part.
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | 2017: /; 2019: clearing - partial clearance of the area; 2020: clearing - completion
Deadline | about 3 years without intervention | 2019: 4,5/2019; 2020: 11/2020
Area | 1.7714 | 2019: 0.6; 2020: 0.6
Intervention | All previous activities were carried out by the landowner outside of conservation activities. | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline |  |  | 5,6/2018 | 5/2019 | 5,6/2020 | 5/2021 | 5,6/2022 | 9/2023 | 6/2024 | 6/2025 | 9/2026 | 10/2027 | 6/2028
Area |  |  | 1.7714 | 1.7714 | 1.7714 | 1.7714 | 1.7714 | 1.7714 | 1.7714 | 1.7714 | 1.7714 | 1.7714 | 1.7714
Intervention |  | / |  | mowing of regrowth (ungrazed vegetation) |  |  |  | 6/2025: mowing of regrowth (ungrazed vegetation); 6/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  |  | 5/2019 |  |  |  | 6/2025: 6/2025; 6/2028: 6/2028
Area |  |  |  | 1.7714 |  |  |  | 6/2025: 1.7714; 6/2028: 1.7714
Intervention |  | / | oregano sowing | thyme planting | thyme planting
Deadline |  |  | 11/2018 | 5,6,10/2019 | 6,11/2020
Area |  |  | 0.0075 | 180 pcs | 195 pcs
Intervention |  | / |  |  | herb sowing
Deadline |  |  |  |  | 11/2020
Area |  |  |  |  | 0.05
TOTAL interventions | 1.7714 | 0 | 1.7714 | 4.1428 | 2.3714 | 1.7714 | 1.7714 | 1.7714 | 1.7714 | 3.5428 | 1.7714 | 1.7714 | 3.5428