## Tisové
Site name | Tisové
Number | 1
Cadastral area | Huslenky
Coordinates | 49.2885247N, 18.0792239E
Location link | https://mapy.cz/s/2IUQ7 | occurrence of large blue on the directly adjoining pasture
Target species | large blue
Target habitats | pasture
TOTAL area | 1.6162 ha
Site characteristics (condition at the start of project): The site adjoins intensive pastures with cattle, forest above the site. No management in recent years. Gradual heavy overgrowth with self-seeding woody plants - hawthorn, blackthorn, etc. Slope of SE exposure, steeper slope in places. Access via a forest track, possible by all-terrain vehicle/tractor in dry weather.
Anticipated management (condition at the start of project): Clearing, preferably in stages (spring/autumn). Focusing on clearing around the perimeter of the site and in heavily stratified places around the site, leaving scattered shrubs and suitable solitary trees (hawthorn, wild rose, etc.) to provide shade/food/shelter for animals. Annual extensive grazing by sheep, optimally outside the summer holidays (otherwise leaving part of the area ungrazed).
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | 2017: /; 2018: clearing - basic clearing along the boundary of the site, to enable grazing; 2019: clearing - partial clearance of the area
Deadline | many years without intervention | 2018: 3,4/2018; 2019: 4,5/2019
Area | 1.6162 | 2018: 0.0885; 2019: 1.0077
Intervention | All previous activities were carried out by the landowner outside of conservation activities. | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline |  |  | 4,5/2018 | 8,9/2019 | 11/2020 | 11/2021 | 11/2022 | 6/2023 | 5/2024 | 9/2025 | 6/2026 | 5/2027 | 10/2028
Area |  |  | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162 | 1.6162
Intervention |  | / | clearing - partial clearance of the area | mowing of regrowth (ungrazed vegetation) | 11/2021: clearing - partial clearance of the area; 11/2022: regrowth mowing; 9/2025: mowing of regrowth (ungrazed vegetation); 10/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  | 10/2018 | 11/2019 | 11/2021: 4/2021; 11/2022: 4/2022; 9/2025: 10/2025; 10/2028: 10/2028
Area |  |  | 0.52 | 1.6162 | 11/2021: 0.45; 11/2022: 1.6162; 9/2025: 1.6162; 10/2028: 1.6162
Intervention |  | / | thyme planting | thyme planting | 11/2021: thyme planting
Deadline |  |  | 10/2018 | 5,6,9,10/2019 | 11/2021: 6/2021
Area |  |  | 40 pcs | 200 pcs | 11/2021: 50 pcs
Intervention |  | / | yellow-rattle sowing
Deadline |  |  | 11/2018
Area |  |  | 0.12
Intervention |  | / | oregano sowing
Deadline |  |  | 11/2018
Area |  |  | 0.0075
TOTAL interventions | 1.6162 | 0 | 2.3522 | 4.2401 | 1.6162 | 2.0662 | 3.2324 | 1.6162 | 1.6162 | 3.2324 | 1.6162 | 1.6162 | 3.2324