## Hluboké
Site name | Hluboké
Number | 7
Cadastral area | Halenkov
Coordinates | 49.3296414N, 18.1435889E
Location link | https://mapy.cz/s/2IY5R | occurrence of ants of the Myrmica genus on the site, the occurrence of large blue at a distance of 600 m
Target species | large blue
Target habitats | pasture
TOTAL area | 1.5565 ha
Site characteristics (condition at the start of project): South to south-west steep slope, formerly juniper pasture, now heavily overgrown. A forest above the site. Overgrowth with blackthorn and self-seeding conifers (spruce, pine), the lower part of the site is wetter and more trophic.
Anticipated management (condition at the start of project): Gradual clearing and opening of junipers, removal of blackthorn bushes. Annual extensive sheep grazing on the entire area.
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | 2018: clearing - basic clearing along the boundary of the site, part of the area; 2019: clearing - partial clearance of the area
Deadline | about 2 years without intervention | 2018: 4/2018; 2019: 4,5/2019
Area | 1.5565 | 2018: 0.31; 2019: 1.2465
Intervention | All previous activities were carried out by the landowner outside of conservation activities. | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline |  | 10/2017 | 4,5/2018 | 7,8/2019 | 9,10/2020 | 6/2021 | 9, 10/2022 | 5/2023 | 9/2024 | 10/2025 | 5/2026 | 9/2027 | 10/2028
Area |  | 1.5565 | 1.5565 | 1.5565 | 1.5565 | 1.5565 | 1.5565 | 1.5565 | 1.5565 | 1.5565 | 1.5565 | 1.5565 | 1.5565
Intervention |  |  | mowing of regrowth (ungrazed vegetation) | mowing of regrowth (ungrazed vegetation) | mowing of regrowth (ungrazed vegetation) |  | mowing of regrowth (ungrazed vegetation) | 10/2025: mowing of regrowth (ungrazed vegetation); 10/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  | 5/2018 | 8/2019 | 11/2020 |  | 4/2022 | 10/2025: 10/2025; 10/2028: 10/2028
Area |  |  | 1.05 | 1.5565 | 1.5565 |  | 1.5565 | 10/2025: 1.5565; 10/2028: 1.5565
Intervention |  |  | thyme planting | thyme planting | thyme planting
Deadline |  |  | 10/2018 | 6,9,10/2019 | 11/2020
Area |  |  | 40 pcs | 120 pcs | 100 pcs
Intervention |  |  | yellow-rattle sowing |  | herb sowing
Deadline |  |  | 11/2018 |  | 11/2020
Area |  |  | 0.35 |  | 0.05
Intervention |  |  | oregano sowing
Deadline |  |  | 11/2018
Area |  |  | 0.0075
TOTAL interventions | 1.5565 | 1.5565 | 3.274 | 4.3595 | 3.163 | 1.5565 | 3.113 | 1.5565 | 1.5565 | 3.113 | 1.5565 | 1.5565 | 3.113