## List1
Site name | Zděchov
Number | 14
Cadastral area | Zděchov
Coordinates | 49.2516111N, 18.0804836E
Location link | https://mapy.cz/turisticka?vlastni-body&x=18.0801296&y=49.2511559&z=17&ut=Zd%C4%9Bchov&uc=9pWXvx8Iyl&ud=49%C2%B015%275.800%22N%2C%2018%C2%B04%2749.741%22E
Target species | large blue
Target habitats | thyme pasture
Planned area of the site (potential) | 5
Area for the given year TOTAL (ha) | 4.9
Site characteristics: These are meadows and former pastures divided by spinneys. A west-facing slope, which is overgrown in places and in others consists of old orchards or juniper pasture. In the past, part of the overgrown juniper pasture with thyme was cleared by the tenants due to the shading of their house by the trees that were located on the site.
Anticipated management: On part of the site, mosaic extensive grazing takes place during May and then during August-October. Part of the site is mowed with light machinery (0.5 ha), 2.2 ha is mowed by hand in September.
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing |  |  | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing | hand mowing
Deadline | 6-7/2016 | 8-9/2017 | 8-9/2018 | 8-9/2019 | 8-9/2020 |  |  | 8-9/2023 | 8-9/2024 | 8-9/2025 | 8-9/2026 | 8-9/2027 | 8-9/2028
Area | 2.15 | 2.2 | 2.7 | 2.7 | 2.7 |  |  | 2.7 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7
Intervention | In 2016, a juniper pasture with an area of 2.15 ha was cut on the site, the management was not suitable for protected insect species. As the potential of the site for the occurrence of the large blue butterfly was proven, the site was added to the project in 2017 and gradually expanded. Management was adjusted to suit the occurrence of specially protected species of butterflies and the mowing date was adjusted. |  |  | mosaic extensive grazing | mosaic extensive grazing | mosaic extensive grazing | mosaic extensive grazing | mosaic extensive grazing | mosaic extensive grazing | mosaic extensive grazing | mosaic extensive grazing | mosaic extensive grazing | mosaic extensive grazing
Deadline |  |  |  | 5,8-9/2019 | 5,8-9/2020 | 5,8-9/2021 | 5,8-9/2022 | 5,8-9/2023 | 5,8-9/2024 | 5,8-9/2025 | 5,8-9/2026 | 5,8-9/2027 | 5,8-9/2028
Area |  |  |  | 2.2 | 2.2 | 2.7 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85
Intervention
Deadline
Area
TOTAL interventions | 2.15 | 2.2 | 2.7 | 4.9 | 4.9 | 2.7 | 1.85 | 4.55 | 4.55 | 4.55 | 4.55 | 4.55 | 4.55