## 11-Ve Vlčí
Site name | Ve Vlčí (Jamárovo)
Number | 11
Cadastral area | Vyškovec
Coordinates | 48.9282172N, 17.8623789E
Location link | https://mapy.cz/s/kejoparaku
Target species | clouded Apollo
Target habitats | grazing grove
Planned area of the site (potential) | 10 ha
Area for the given year TOTAL (ha) | 6.940 ha
Site characteristics: Several separate locations in the vicinity of Ve Vlčí Nature Reserve, oriented mainly north to north-west. Most of the areas have not been managed for more than 30 years, with the exception of one where self-seeding plant clearing was carried out in 2010. It was then continuously managed at the owner's expense until 2016, after which no further management was done. A varied range of adjacent ecosystems in the immediate vicinity increases its attractiveness and is promising for clouded Apollo.
Anticipated management Opening the existing vegetation and removal of a substantial part of regrowing shrubs with the aim of creating a more open grazing grove. Subsequent management will take place by grazing followed by mowing of ungrazed vegetation.
Implemented/planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023-2028
Intervention | area without intervention for at least 30 years |  | self-seeding plant clearing | self-seeding plant clearing | self-seeding plant clearing | merging with the plot below | merging with the plot below | merging with the plot below
Deadline |  | 2018: 10-12/2018; 2019: 9-11/2019; 2020: 9-11/2020
Area - Michalec |  | 2018: 0.692; 2019: 0.363; 2020: 0.215
Intervention | area without intervention for at least 30 years |  |  | grazing | grazing | grazing | grazing | transfer to LPIS
Deadline |  | 2019: 10-12/2019; 2020: 8-10/2020; 2021: 8-10/2021; 2022: 8-10/2022
Area - Michalec |  | 2019: 0.69; 2020: 1.268; 2021: 1.272; 2022: 1.268
Intervention | area without intervention for at least 30 years |  |  | self-seeding plant clearing | merging with the plot below | merging with the plot below | merging with the plot below | merging with the plot below
Deadline |  | 2019: 2-3 a 9-11/2019
Area - Kubík |  | 2019: 1.331
Intervention | area without intervention for at least 30 years |  |  | grazing | grazing | grazing | grazing | management
Deadline |  | 2019: 10-12/2019; 2020: 6-9/2020; 2021: 6-9/2021; 2022: 6-9/2022
Area - Kubík |  | 2019: 0.333; 2020: 1.315; 2021: 1.391; 2022: 1.315
Intervention | area without intervention for at least 30 years |  |  | regrowth mowing | merging with the plot above | merging with the plot above | merging with the plot above | merging with the plot above
Deadline |  | 2019: 10-12/2019
Area - Kubík |  | 2019: 0.067
Intervention | area without intervention 20-30 years |  |  | self-seeding plant clearing | grazing | grazing | grazing | management
Deadline |  | 2019: 10-12/2019; 2020: 6-9/2020; 2021: 6-9/2021; 2022: 6-9/2022
Area - Chovancová |  | 2019: 0.75; 2020: 0.75; 2021: 0.904; 2022: 1.144
Intervention | area abandoned 15-20 years ago |  |  | self-seeding plant clearing | regrowth removal | grazing | management paid by the owner | management
Deadline |  | 2019: 10-12/2019; 2020: 6-9/2020; 2021: 6-9/2021
Area - Chovanec |  | 2019: 0.315; 2020: 0.315; 2021: 0.283
Intervention | self-seeding plant clearing from LPM grant title |  |  | self-seeding plant clearing | merging with the plot below | merging with the plot below | merging with the plot below | merging with the plot below
Deadline | 2010 | 2019: 10-12/2019; 2021: 10-12/2021
Area - Sasín | 0.26 | 2019: 1; 2021: 0.9
Intervention | area without intervention for at least 30 years | 2020: grazing; 2021: grazing; 2022: grazing; 2023-2028: maintenance
Deadline |  | 2020: 6-9/2020; 2021: 6-9/2021; 2022: 6-9/2022
Area - Sasín |  | 2020: 1; 2021: 1.016; 2022: 1.001
Intervention | area without intervention for at least 30 years | 2022: regrowth removal; 2023-2028: maintenance
Deadline |  | 2022: 6-9/2022
Area - Karlík |  | 2022: 0.589
Intervention | area without intervention for at least 30 years | 2022: grazing; 2023-2028: maintenance
Deadline |  | 2022: 6-9/2022
Area - Svoboda |  | 2022: 0.24
Intervention | area without intervention for at least 10 years | 2022: regrowth removal; 2023-2028: maintenance
Deadline |  | 2022: 6-9/2022
Area - Záhorová |  | 2022: 0.29
Intervention | 1. removed from LPIS in 2020 / 2. self-seeding plants for 30 years | 2022: grazing and self-seeding plant removal; 2023-2028: maintenance
Deadline |  | 2022: 6-9/2022
Area - Ševčík |  | 2022: 1.083
TOTAL interventions |  | 0 | 0.692 | 4.849 | 4.863 | 5.766 | 6.93 | 0