## Dinotice
Site name | Dinotice
Number | 8
Cadastral area | Halenkov
Coordinates | 49.3270422N, 18.1319697E
Location link | https://mapy.cz/s/2IYoK
Target species | large blue (on site)
Target habitats | pasture
TOTAL area | 1.4764 ha
Site characteristics (condition at the start of project): South-western slope, divided by spinneys. Wood small-reed is aggressively overgrowing the area, which the sheep will not graze. Site without the need for clearing.
Anticipated management (condition at the start of project): Annual extensive sheep grazing on the entire area. Sowing yellow-rattle to supress wood small-reed.
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline | about 3 (?) years without intervention | 10,11/2017 | 9,10/2018 | 8,9/2019 | 11/2020 | 10/2021 | 5,6/2022 | 10/2023 | 10/2024 | 5/2025 | 9/2026 | 6/2027 | 5/2028
Area | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764 | 1.4764
Intervention | Grazing in the past, all previous activities were carried out by the landowner outside of conservation activities. |  |  | mowing of regrowth (ungrazed vegetation) |  | clearing - partial clearance of the area | mowing of regrowth (ungrazed vegetation) | 5/2025: mowing of regrowth (ungrazed vegetation); 5/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  |  | 9/2019 |  | 4/2021 | 4/2022 | 5/2025: 6/2025; 5/2028: 5/2028
Area |  |  |  | 1.4764 |  | 0.1 | 1.4764 | 5/2025: 1.4764; 5/2028: 1.4764
Intervention |  | yellow-rattle sowing | fencing the areas sown with yellow-rattle | thyme planting
Deadline |  | 11/2017 | 4/2018 | 6,10/2019
Area |  | 0.11 |  | 100 pcs
TOTAL interventions | 1.4764 | 1.5864 | 1.4764 | 2.9528 | 1.4764 | 1.5764 | 2.9528 | 1.4764 | 1.4764 | 2.9528 | 1.4764 | 1.4764 | 2.9528