## Chumy
Site name | Bošáca - Chúmy, Peterkové, Zabudišová
Number | 5
Cadastral area | Bošáca
Coordinates | 48.841593N, 17.849787E
Location link | https://goo.gl/maps/7fmPGYE98YFZksDV6
Target species | Colias myrmidone, Lucanus cervus
Target habitats | pasture, forest pasture, coppice forest, change of management
TOTAL area | 36.26 ha
Site characteristics (condition at the start of project): The site is one of the few sites with a confirmed recent occurrence of Colias myrmidone in Biele Karpaty PLA (also Lycaene dispar, Eriogaster catax, Zernthia polyxena); overgrown pastures with sufficiently large trees - fruit trees and oaks. There are oak and beech forests with the occurrence of Lucanus cervus and Rosalia alpina, suitable for coppicing, as well as intensively mowed monoculture grasslands. The affected areas were without management for a long time and were heavily overgrown with self-seeding woody plants - hawthorn, blackthorn, oak, etc. Slope exposure: S, SW, W, NW, steeper slope and undulating terrain. Access by local, field and forest roads, by an off-road vehicle/tractor in dry weather, in frost.
Management during the project: Clearing continuous areas of self-seeding woody plants, clearing wide transitions and edges of meadows and forests, leaving old trees (oaks, fruit trees) for scattered grazing, including larger groups of trees for forest grazing, creating forest edges. Mosaic mowing and extensive grazing by cattle, horses, sheep and goats in cooperation with local stakeholders. Planted trees to divide large blocks of monoculture meadows, sowing sainfoins.
Planned management
| 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | without intervention - coppice forest | without intervention - coppice forest | without intervention - coppice forest | without intervention - coppice forest | without intervention - coppice forest | without intervention - coppice forest
Deadline | 0 | 0 | 0 | 0 | 0 | 0
Area | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Intervention | grazing | grazing | grazing | grazing | grazing | grazing
Deadline | 5-10/2023 | 5-10/2024 | 5-10/2025 | 5-10/2026 | 5-10/2027 | 5-10/2028
Area | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
Intervention | mowing of regrowth and ungrazed vegetation | mowing of regrowth and ungrazed vegetation | mowing of regrowth and ungrazed vegetation | mowing of regrowth and ungrazed vegetation | mowing of ungrazed vegetation | mowing of ungrazed vegetation
Deadline | 10-12/2023 | 02-03, 10-12/2024 | 02-03, 10-12/2025 | 02-03, 10-12/2026 | 10-12/20267 | 10-12/2028
Area | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
Intervention | mowing of extensified areas | mowing of extensified areas | mowing of extensified areas | mowing of extensified areas | mowing of extensified areas | mowing of extensified areas
Deadline | 6-9/2023 | 6-9/2024 | 6-9/2025 | 6-9/2026 | 6-9/2027 | 6-9/2028
Area | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1
Intervention |  | management of tree planting (fence repair, treatment/replacement of trees) |  | management of tree planting (fence repair, treatment/replacement of trees) |  | management of tree planting (fence repair, treatment/replacement of trees)
Deadline |  | 10-12/24 |  | 02-03, 10-12/26 |  | 02-03, 10-12/28
Area
TOTAL interventions | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4