## List1
Site name | Lušová - Stařanská
Number | 11
Cadastral area | Halenkov
Coordinates | 49.3611647N, 18.1406014E
Location link | https://sk.mapy.cz/zakladni?vlastni-body&x=18.1429617&y=49.3535058&z=15&ut=Lu%C5%A1ov%C3%A1%20-%20Sta%C5%99ansk%C3%A1&uc=9peURx8ps1&ud=49%C2%B021%2740.193%22N%2C%2018%C2%B08%2726.165%22E
Target species | large blue
Target habitats | thyme pasture
Planned area of the site (potential) | 2.4
Area for the given year TOTAL (ha) | 2.4
Site characteristics: These are meadows with a south-eastern exposure, located partly on a ridge. The site is divided by a spruce forest. There are junipers and thyme in abundance on the site, in some places the site is overgrown with spruce, which is being cleared. Even in the 1950s, there were relatively large pastures here. After that, the meadows were gradually overgrown and degraded until cultivation started here again.
Anticipated management: Gradual mosaic grazing by sheep (May - June and then at the end of August). Grazing is rotated with mowing, which takes place in late August and early September. The plots are regularly rotated.
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | grazing, mowing | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline | summer 2017 |  | 5-10/2018 (with an interruption over large blue development) | 5-10/2019 (with an interruption over large blue development) | 5-10/2020 (with an interruption over large blue development) | 5-10/2021 (with an interruption over large blue development) | 5-10/2022 (with an interruption over large blue development) | 5-10/2023 (with an interruption over large blue development) | 5-10/2024 (with an interruption over large blue development) | 5-10/2025 (with an interruption over large blue development) | 5-10/2026 (with an interruption over large blue development) | 5-10/2027 (with an interruption over large blue development) | 5-10/2028 (with an interruption over large blue development)
Area | 2.4 |  | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9
Intervention | In the last 10 years, the owner started mowing the site and some spruce trees were cut. In 2017, following a change of ownership, grazing was largely restored here to prevent further overgrowth of the pasture. In 2017, the site was re-grazed and partially mowed. The site was added in 2018 due to the potential occurrence of large blue butterfly. Management has been adjusted to suit the target species and grazing and mowing dates have been adjusted. Management intensity was also changed, as it was too extensive in places and the site was overgrown. | / | mowing | mowing | mowing | mowing | mowing | mowing | mowing | mowing | mowing | mowing | mowing
Deadline |  |  | 8-9/2018 | 8-9/2019 | 8-9/2020 | 8-9/2021 | 8-9/2022 | 8-9/2023 | 8-9/2024 | 8-9/2025 | 8-9/2026 | 8-9/2027 | 8-9/2028
Area |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Intervention |  | 2017: /; 2020: clearing
Deadline |  | 2020: autumn 2020
Area |  | 2020: 0.014
TOTAL interventions | 2.4 | 0 | 2.4 | 2.4 | 2.414 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4