## Orság
Site name | Karolinka - Orság
Number | 3
Cadastral area | Karolinka
Coordinates | 49.3542856N, 18.2408378E
Location link | https://mapy.cz/s/2IUWe
Target species | large blue (on site)
Target habitats | pasture
TOTAL area | 0.6740 ha
Site characteristics (condition at the start of project): Steep southern slope. Plum trees planted in the lower part, about 10 years old. A forest is adjoined to the site, self-seeding plants are spreading in the upper part (spruce, blackthorn). A dry habitat with the occurrence of thyme. Hawthorn and wild rose grow individually over the area.
Anticipated management (condition at the start of project): Clearing especially around the perimeter of the site. Annual extensive grazing by sheep, optimally outside the summer holidays (otherwise leaving part of the area ungrazed). Leaving suitable solitary bushes in the area.
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | 2017: /; 2018: scrub clearing
Deadline | about 3 years without intervention | 2018: 3,4/2018
Area | 0.674 | 2018: 0.14
Intervention | All previous activities were carried out by the landowner outside of conservation activities. | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline |  |  | 5,6/2018 | 6/2019 | 9,10/2020 | 9,10/2021 | 10/2022 | 9/2023 | 6/2024 | 5/2025 | 10/2026 | 9/2027 | 6/2028
Area |  |  | 0.674 | 0.674 | 0.674 | 0.674 | 0.674 | 0.674 | 0.674 | 0.674 | 0.674 | 0.674 | 0.674
Intervention |  | / |  | mowing of regrowth (ungrazed vegetation) | mowing of regrowth (ungrazed vegetation) |  | 5/2025: mowing of regrowth (ungrazed vegetation); 6/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  |  | 6/2019 | 11/2020 |  | 5/2025: 6/2025; 6/2028: 10/2028
Area |  |  |  | 0.674 | 0.674 |  | 5/2025: 0.674; 6/2028: 0.674
Intervention |  | / |  |  |  | thyme planting
Deadline | [5 empty] | 9/2021
Area | [5 empty] | 30 pcs
TOTAL interventions | 0.674 | 0 | 0.814 | 1.348 | 1.348 | 0.674 | 0.674 | 0.674 | 0.674 | 1.348 | 0.674 | 0.674 | 1.348