## 9-Súdeniska
Site name | Súdeniska
Number | 9
Cadastral area | Suchá Loz
Coordinates | 48.9325028N, 17.7171961E
Location link | https://mapy.cz/s/remonozujo
Target species | dusky large blue, clouded Apollo
Target habitats | open grazing grove
Planned area of the site (potential) | 3.7 ha
Area for the given year TOTAL (ha) | 3.061 ha
Site characteristics: North-west-oriented dissected site, which was continuously managed over an area of 1.781 ha until 2015 and 0.117 ha until 2017. However, these areas were gradually closed by expanding self-seeding woody plants. It changed when the land was taken over for use by another contractor, the vegetation was restored and further management is thus ensured.
Anticipated management: Opening of the existing vegetation and removal of a substantial part of the regrowing bushes with the aim of creating a more open grazing grove. Subsequent management will take place by grazing followed by mowing the ungrazed vegetation.
Implemented/planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023-2028
Intervention | hand mowing from PPK grant title |  | self-seeding plant clearing | grazing | grazing; part of area included in LPIS | included in LPIS - grazing | included in LPIS - grazing | included in LPIS - grazing
Deadline | 2015 / 2017 | 2018: 10-12/2018; 2019: 8-9/2019; 2020: 8-9/2020
Area | 1.781 / 0.117 | 2018: 3.011; 2019: 3.061; 2020: 1.231
Intervention
Deadline
Area
Intervention
Deadline
Area
TOTAL interventions |  | 0 | 3.011 | 3.061 | 1.231 | 0 | 0