## 49-Hrozenkov
Site name | Hrozenkov
Number | 49
Cadastral area | Starý Hrozenkov
Coordinates 1 | 48°58'8.593"N, 17°51'57.958"E
Coordinates 2 | 48°58'23.457"N, 17°51'46.391"E
Coordinates 3 | 48°57'53.183"N, 17°51'28.701"E
Location link | https://mapy.cz/s/casacudapa
Target species | stag beetle, clouded Apollo
Target habitats | pasture, grove, orchards
Planned area of the site (potential) | 10 h
Area for the given year TOTAL (ha) | 4.885 ha
Site characteristics: The first part is a previously managed grazed orchard, which was excluded from the LPIS due to the diverse vegetation structure, which is contrary to the rules of the SAIF. The second part is a long valley with the character of a forest park, which divides the surrounding pastures and provides a refuge for invertebrates and small vertebrates. The third part is a sunny slope that was formerly part of the handling areas of the quarry. There are random piles of stones and scattered vegetation on the site. Suitable for thermophilous species.
Anticipated management: Self-seeding plant removal leading to the creation of grazed, varied habitats with a diverse vegetation structure.
Implemented/planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023-2028
Intervention | first part was previously managed with the support of subsidies from SAIF | grazing from LPIS | grazing from LPIS | grazing from LPIS | management by the user | without management | grazing | grazing by the owner
Deadline |  | 2022: 7-11/2022
Area 1 |  | 2022: 3.638
Intervention | second part is randomly managed by the owner | without management | grazing by the owner | without management | mowing by the owner | without management | grazing | grazing by the owner
Deadline |  | 2022: 7-11/2022
Area 2 |  | 2022: 0.416
Intervention | third part is a sunny slope abandoned for 20 years | 2022: self-seeding plant removal; 2023-2028: grazing
Deadline |  | 2022: 11/2022
Area 3 |  | 2022: 0.831; 2023-2028: 0.83
TOTAL interventions |  | 0 | 0 | 0 | 0 | 0 | 4.885 | 0.83