## Kovář
Site name | Hovězí - Kovář
Number | 5
Cadastral area | Hovězí
Coordinates | 49.3127783N, 18.0633433E
Location link | https://mapy.cz/s/2IWD5
Target species | large blue (on site)
Target habitats | pasture
TOTAL area | 0.4673
Site characteristics (condition at the start of project): Mainly southern slope. The part near the stream is wetter, in the upper part there are old fruit trees. There are places with bramble and raspberry growing over the area. Occurrence of thyme and oregano.
Anticipated management (condition at the start of project): Clearing/mowing of regrowth around the perimeter of the site and reduction of bramble and raspberry. Annual extensive grazing by sheep, optimally outside the summer holidays (otherwise leaving part of the area ungrazed).
Implemented management | [7 empty] | Planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline | about 5 (?) years without intervention | 11/2017 | 10/2018 | 4,5/2019 | 6/2020 | 6/2021 | 6/2022 | 10/2023 | 5/2024 | 9/2025 | 10/2026 | 5/2027 | 5/2028
Area | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673 | 0.4673
Intervention | Grazing in the past, all previous activities were carried out by the landowner outside of conservation activities. | / | mowing of regrowth (ungrazed vegetation) | mowing of regrowth (ungrazed vegetation) | 6/2020: mowing of regrowth (ungrazed vegetation); 6/2021: clearing - partial clearance of the area; 9/2025: mowing of regrowth (ungrazed vegetation); 5/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  | 11/2018 | 5/2019 | 6/2020: 7/2020; 6/2021: 4/2021; 9/2025: 10/2025; 5/2028: 16/2028
Area |  |  | 0.4673 | 0.4673 | 6/2020: 0.4673; 6/2021: 0.35; 9/2025: 0.4673; 5/2028: 0.4673
Intervention |  | / |  |  | 6/2021: thyme planting; 10/2023: /
Deadline |  |  |  |  | 6/2021: 9/2021
Area |  |  |  |  | 6/2021: 75 pcs
TOTAL interventions | 0.4673 | 0.4673 | 0.9346 | 0.9346 | 0.9346 | 0.8173 | 0.4673 | 0.4673 | 0.4673 | 0.9346 | 0.4673 | 0.4673 | 0.9346