## 16-Třešňůvka
Site name | Třešňůvka
Number | 16
Cadastral area | Rudimov
Coordinates | 49.0870944N, 17.8273658E
Location link | https://mapy.cz/s/rocumabefu
Target species | stage beetle, clouded Apollo
Target habitats | grazing forest
Planned area of the site (potential) | 8 ha
Area for the given year TOTAL (ha) | 7.949 ha
Site characteristics: Třešňůvka stream valley, oriented from south-east to south-west. Original fields, orchards, meadows, and pastures. Most of the area abandoned 20-40 years ago. Due to its scope, variety and dissection, this is a very important site, which in its character can become a grazing forest.
Anticipated management: Opening the existing vegetation with subsequent extensive grazing.
Implemented/planned management
| Last intervention before the Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023-2028
Intervention | 20-40 years without management | 2019: self-seeding plant clearing
Deadline |  | 2019: 2-3/2019
Area |  | 2019: 7.741
Intervention |  |  |  | grazing | grazing | 2 x grazing | grazing | grazing
Deadline |  | 2019: 7-9/2019; 2020: 7-9/2020; 2021: 7-9/2021; 2022: 7-9/2022
Area |  |  |  | 7.741 | 7.741 | 15.891 | 7.949 | 4
Intervention
Deadline
Area
TOTAL interventions |  | 0 | 0 | 15.482 | 7.741 | 15.891 | 7.949 | 4