## Miloňov
Site name | Miloňov
Number | 2
Cadastral area | Velké Karlovice
Coordinates | 49.3727739N, 18.3237233E
Location link | https://mapy.cz/s/2IUSg
Target species | large blue (on site)
Target habitats | pasture
TOTAL area | 2.2258 ha
Site characteristics (condition at the start of project): Very steep southern slope. About 30 years without management, but still a very well-preserved condition - a poor and dry habitat with an abundance of thyme. Self-seeding trees spread individually or in groups over the area. Difficult access to the site - only in dry weather around the owner's house.
Anticipated management (condition at the start of project): Clearing especially around the perimeter of the site. Selective clearing of self-seeding woody plants, leaving scattered bushes and suitable solitary trees (hawthorn, wild rose, etc.) to provide shade/food/shelter for animals. Annual extensive grazing by sheep, optimally outside the summer holidays (otherwise leaving part of the area ungrazed).
Implemented management | [7 empty] | Planned management
| Last intervention before Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Intervention | / | 2017: /; 2019: clearing - clearance of the area
Deadline | about 10 years without intervention | 2019: 4,5/2019
Area | 2.2258 | 2019: 2.2258
Intervention | All previous activities were carried out by the landowner outside of conservation activities. | / | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing | grazing
Deadline |  |  | 9,10/2018 | 5,6/2019 | 9,10/2020 | 10/2021 | 10/2022 | 5/2023 | 9/2024 | 10/2025 | 5/2026 | 6/2027 | 9/2028
Area |  |  | 2.2258 | 2.2258 | 2.2258 | 2.2258 | 2.2258 | 2.2258 | 2.2258 | 2.2258 | 2.2258 | 2.2258 | 2.2258
Intervention |  | / |  | mowing of regrowth (ungrazed vegetation) | mowing of regrowth (ungrazed vegetation) | 10/2025: mowing of regrowth (ungrazed vegetation); 9/2028: mowing of regrowth (ungrazed vegetation)
Deadline |  |  |  | 6/2019 | 11/2020 | 10/2025: 10/2025; 9/2028: 10/2028
Area |  |  |  | 2.2258 | 2.2258 | 10/2025: 2.2258; 9/2028: 2.2258
Intervention |  | / |  | thyme planting
Deadline |  |  |  | 6,10/2019
Area |  |  |  | 180
TOTAL interventions | 2.2258 | 0 | 2.2258 | 6.6774 | 4.4516 | 2.2258 | 2.2258 | 2.2258 | 2.2258 | 4.4516 | 2.2258 | 2.2258 | 4.4516